Product Innovation Progress Report

- Date: 30th Jan / 06th Feb 2025

- Attendees: Product innovation committee

- Agenda

- Presentation of 2025 BSC OKRs

- New / Revamp Product Screening

- Action Plan Preparation

- PRESENTATION OF 2025 COMPANY OKRs

- The committee reviewed and discussed the company’s 2025 OKRs, focusing on Objectives and key results and expected outcomes.

- Emphasis was placed on aligning product innovation efforts with business growth, customer experience, and market competitiveness.

- Key insights were shared regarding revenue targets, markets expansion, and digital transformation initiatives.

- PRODUCT SCREENING

- A list of Thirteen products, new and revamp products ideas was presented for evaluation.

- The committee applied predefined screening criteria, including market demand, feasibility, profitability, and alignment with strategic goals.

- Only four products ideas were selected to be evaluated to proceed in the next phases.

- The Products ideas are;

- Network VAS: (CCTV, IOT Devices, AD, Archive…)

- Education one-stop center: (Academic documents, E-learning/Online    course, Knowledge sharing….)

- Advert as a service: (Through captive portal)

- VOIP service revamp.

For each product to advance to the next phase, we agreed that it will be evaluated based on the following checklist.

| CRITERIA |  | NET. VAS | EDUC. OSC | ADVERT AS | VOIP REVAMP |
| --- | --- | --- | --- | --- | --- |
| 1 | Technical feasibility (Is it doable?) |  |  |  |  |
| 2 | Target market? (ROI) |  |  |  |  |
| 3 | Timeline |  |  |  |  |
| 4 | Financial Study |  |  |  |  |
| 5 | Resources |  |  |  |  |

So far, only one product “Network Valu-Added Service,” has successfully passed but two products will proceed simultaneously.

- ACTION PLAN – 1st Product

| KEY ACTION / TASKS | TIMELINE | RESPONSABILITIES |
| --- | --- | --- |
| Business Case Draft | 13/02/2025 |  |
| Final Business Case | 20/02/2025 |  |
| First Approval | 27/02/2025 |  |
| Approved Solution (Final approval) | 31/03/2025 |  |
| Procurement | 01 – 30 /04/2025 |  |
| Development, Testing and Launch | May & June |  |
| On Market | 1/07/2025 |  |

2nd Product

| KEY ACTION / TASKS | TIMELINE | RESPONSABILITIES |
| --- | --- | --- |
| Approved Solution | 30/06/2025 |  |
| Procurement | 01 – 30 /07/2025 |  |
| Development, Testing and launch | Aug 2025 |  |
| On Market | 1/09/2025 |  |